PROJECT PLAN – MULTI-SPECIALITY HOSPITAL WEBSITE

1. PROJECT OBJECTIVES

• Build a professional, modern hospital website inspired by leading multi-speciality institutes.

• Enable easy access to key services: Find a Doctor, Specialities, Appointments, Emergency Care.

• Support patient care information, international patient services, careers, and SEO-friendly content.

2. HIGH-LEVEL SCOPE (PHASE 1)

1. Home Page

– Hero banner, emergency contacts, appointment CTA.

– Specialities, doctors, statistics, testimonials.

2. About Us

– Hospital overview, mission/vision, management, infrastructure.

3. Specialities / Departments

– Speciality listing and detailed department pages.

4. Doctors / Find a Doctor

– Filters, doctor profiles, qualifications, appointment option.

5. Patient Care

– Billing, insurance, pharmacy, diagnostics, ICU, visiting hours.

6. International Patients

– Visa guidance, airport pickup, stay assistance.

7. Preventive Health Packages

– Package list, inclusions, pricing.

8. Contact & Locations

– Addresses, maps, emergency numbers, enquiry form.

9. Appointments & Enquiry Forms

– Appointment request, general inquiries.

10. Careers

– Job listings, CV upload.

11. News / Events / Blog

– Articles and updates.

12. Utility Pages

– Privacy Policy, Terms, Disclaimer.

Phase 2 Enhancements

• Patient portal, online bill payment, chatbot, multilingual content.

3. ROLES & RESPONSIBILITIES

• Product Owner • Project Manager • UX/UI Designer • Frontend Developer

• Backend Developer • Content Writer • SEO Specialist • QA Tester • DevOps

4. PHASED PROJECT PLAN

Phase 1 – Discovery (1–2 Weeks)

• Stakeholder interviews and requirement finalization.

• Site map and feature prioritization.

Phase 2 – Information Architecture & UX (1–2 Weeks)

• User journey mapping, wireframes for all key pages.

Phase 3 – UI Design (2–3 Weeks)

• Branding, color palette, typography, responsive design mockups.

Phase 4 – Technology Architecture & Setup (1 Week)

• Decide CMS vs Custom build, hosting setup, CI/CD.

Phase 5 – Frontend Development (3–4 Weeks)

• Create responsive pages and shared UI components.

Phase 6 – Backend & CMS Integration (3–4 Weeks)

• Configure content models, forms, dynamic pages, admin dashboards.

Phase 7 – Content & SEO (2–3 Weeks)

• Drafting website content, metadata, analytics setup.

Phase 8 – Testing & UAT (1–2 Weeks)

• Functional, performance, responsive testing, stakeholder review.

Phase 9 – Launch (1 Week)

• Go-live deployment, DNS, admin training.

Phase 10 – Post Launch Support

• 1–3 months maintenance and Phase 2 planning.

5. TIMELINE SUMMARY

Weeks 1–2: Discovery, IA & UX

Weeks 3–5: UI Design

Week 6: Tech Setup

Weeks 7–10: Development

Weeks 9–11: Content & SEO

Weeks 11–12: Testing & UAT

Week 13: Launch